## Cover
Operation Iron Shield (OIS-CMS)
Plan of Action and Milestones (POA&M)
NIST RMF Step 5 · NIST SP 800-53 Rev 5 · AWS GovCloud · CUI System
System Name | Operation Iron Shield Case Management System (OIS-CMS)
System ID | OIS-CMS-001
Impact Level | MODERATE — per FIPS 199
Control Baseline | NIST SP 800-53 Rev 5 Moderate
Operating Environment | AWS GovCloud (FedRAMP High)
ISSO | Ashley Miller
Date Prepared | July 2026
Version | 1.0
Total Findings | 19
HIGH Risk Findings | 10
MODERATE Risk Findings | 9
Phase 1 Target | 30 days — 7 policy documents
Phase 2 Target | 60 days — 5 operational plans and configurations
Phase 3 Target | 90 days — 6 procedures and documentation gaps
POA&M Status | Active — All Findings Open — Remediation Planning Underway
HIGH — Immediate action required within 30-90 days
MODERATE — Action required within 90-180 days
Open — Finding identified, no remediation work started
In Progress — Active remediation underway
Closed — All milestones complete, evidence documented, AO notified

## POA&M Tracker
Operation Iron Shield (OIS-CMS) — Plan of Action and Milestones (POA&M)
NIST RMF Step 5 · 19 Findings · 3 Remediation Phases · July 2026 · Version 1.0
POA&M ID | Originating Control | Weakness Description | Risk Rating | Scheduled Completion | Milestones | Responsible POC | Resources Required | Status | Progress Notes | Date Closed
Phase 1 — Policy Documents (HIGH Priority)
OIS-POA-001 | AC-1 | No OIS program-level access control policy exists. The system has been operating without a formally documented, approved, and disseminated access control policy governing purpose, scope, roles, responsibilities, and compliance obligations. | HIGH | 30 days from authorization kickoff | 1. Identify all stakeholders — ISSO, Program Manager, Legal/Compliance advisor 2. Review NIST SP 800-53 AC-1, FISMA, FedRAMP, 32 CFR Part 2002, DoDI 8510.01 requirements 3. Draft OIS access control policy covering purpose, scope, roles, responsibilities, and compliance 4. Conduct internal stakeholder review and incorporate feedback 5. Submit draft to Program Manager and senior leadership for formal review 6. Obtain signed approval from the Authorizing Official or designated approver 7. Disseminate approved policy to all OIS-CMS personnel with documented acknowledgment 8. Update SSP Section 7 and SCTM to reflect AC-1 as Implemented 9. File policy document in the OIS authorization package 10. Close OIS-POA-001 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ Legal/Compliance Advisor ¦ NIST SP 800-53 AC-1 Guidance ¦ FISMA/FedRAMP/32 CFR Part 2002/DoDI 8510.01 Reference Documentation ¦ Document Management System | Open | Finding identified during SCTM development. No access control policy exists for OIS-CMS. Teams being assembled to begin policy drafting. Remediation planning underway.
OIS-POA-003 | IA-1 | No OIS program-level identification and authentication policy exists. The system has been operating without a formally documented policy governing authentication requirements, responsibilities, and compliance obligations. | HIGH | 30 days from authorization kickoff | 1. Identify stakeholders — ISSO, Program Manager, Legal/Compliance advisor, IAM team lead 2. Review NIST SP 800-53 IA-1, PIV/CAC federal requirements, FedRAMP IA policy requirements 3. Draft OIS identification and authentication policy 4. Conduct internal review and incorporate stakeholder feedback 5. Submit to Program Manager and senior leadership for formal approval 6. Obtain signed approval from authorized approver 7. Disseminate to all OIS-CMS personnel with documented acknowledgment 8. Update SSP and SCTM to reflect IA-1 as Implemented 9. Close OIS-POA-003 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ IAM Team Lead ¦ Legal/Compliance Advisor ¦ NIST SP 800-53 IA-1 Guidance ¦ PIV/CAC Federal Requirements Documentation | Open | Finding identified during SCTM development. No authentication policy exists for OIS-CMS. Prerequisite for full IA-5 authenticator management procedures implementation. Teams being assembled.
OIS-POA-005 | AU-1 | No OIS program-level audit and accountability policy exists. The system has been generating audit logs without a formally documented policy governing audit requirements, review responsibilities, and retention obligations. | HIGH | 30 days from authorization kickoff | 1. Identify stakeholders — ISSO, Program Manager, Security Operations team 2. Review NIST SP 800-53 AU-1, FISMA audit requirements, FedRAMP logging requirements 3. Draft OIS audit and accountability policy 4. Conduct internal review and incorporate feedback 5. Obtain formal approval from Program Manager and senior leadership 6. Disseminate to all OIS-CMS personnel with documented acknowledgment 7. Update SSP and SCTM to reflect AU-1 as Implemented 8. Close OIS-POA-005 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ Security Operations Team ¦ NIST SP 800-53 AU-1 Guidance ¦ FISMA Audit Requirements ¦ FedRAMP Logging Requirements Documentation | Open | Finding identified during SCTM development. Audit logging is operational through CloudTrail and CloudWatch but no governing policy exists. Prerequisite for AU-6 review schedule and AU-11 retention policy.
OIS-POA-008 | SC-1 | No OIS program-level system and communications protection policy exists. Transmission encryption and boundary protection controls are operational but without a governing policy document. | HIGH | 30 days from authorization kickoff | 1. Identify stakeholders — ISSO, Program Manager, Network/Infrastructure team 2. Review NIST SP 800-53 SC-1, OMB M-15-13, FedRAMP SC policy requirements 3. Draft OIS system and communications protection policy 4. Conduct internal review and incorporate feedback 5. Obtain formal approval and disseminate to all personnel 6. Update SSP and SCTM to reflect SC-1 as Implemented 7. Close OIS-POA-008 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ Network/Infrastructure Team ¦ NIST SP 800-53 SC-1 Guidance ¦ OMB M-15-13 ¦ FedRAMP SC Requirements Documentation | Open | Finding identified during SCTM development. TLS, boundary protection, and encryption controls are operational. Governing policy document does not exist. Prerequisite for SC-12 key rotation procedures.
OIS-POA-010 | IR-1 | No OIS program-level incident response policy exists. The seven phase IR lifecycle is understood operationally but has never been formally documented in a governing policy. | HIGH | 30 days from authorization kickoff | 1. Identify stakeholders — ISSO, Program Manager, IR team, Legal/Compliance 2. Review NIST SP 800-53 IR-1, NIST SP 800-61 Rev 2, US-CERT reporting requirements 3. Draft OIS incident response policy including US-CERT one hour reporting obligation 4. Conduct internal review and incorporate feedback 5. Obtain formal approval from Program Manager and senior leadership 6. Disseminate to all OIS-CMS personnel with documented acknowledgment 7. Update SSP and SCTM to reflect IR-1 as Implemented 8. Close OIS-POA-010 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ Incident Response Team ¦ Legal/Compliance Advisor ¦ NIST SP 800-53 IR-1 ¦ NIST SP 800-61 Rev 2 ¦ US-CERT Reporting Requirements | Open | Finding identified during SCTM development. Highest operational risk finding — no IR policy means incident response has no formal authority or documented US-CERT reporting obligation. Prerequisite for IR-4, IR-5, and IR-8.
OIS-POA-014 | CM-1 | No OIS program-level configuration management policy exists. System configurations are in place but without a governing policy establishing requirements, responsibilities, and change control procedures. | HIGH | 30 days from authorization kickoff | 1. Identify stakeholders — ISSO, Program Manager, AWS administrators, application team 2. Review NIST SP 800-53 CM-1, FedRAMP CM requirements, change control standards 3. Draft OIS configuration management policy 4. Conduct internal review and incorporate feedback 5. Obtain formal approval and disseminate to all personnel 6. Update SSP and SCTM to reflect CM-1 as Implemented 7. Close OIS-POA-014 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ AWS Administrators ¦ Application Team ¦ NIST SP 800-53 CM-1 Guidance ¦ FedRAMP CM Requirements | Open | Finding identified during SCTM development. Configuration settings are operationally correct but no governing policy exists. Prerequisite for CM-2 baseline configuration and CM-6 configuration settings documentation.
OIS-POA-017 | RA-1 | No OIS program-level risk assessment policy exists. Risk assessment activities have been conducted as part of the RMF process but without a formally documented governing policy. | HIGH | 30 days from authorization kickoff | 1. Identify stakeholders — ISSO, Program Manager, Risk management team 2. Review NIST SP 800-53 RA-1, NIST SP 800-30, FedRAMP RA requirements 3. Draft OIS risk assessment policy 4. Conduct internal review and incorporate feedback 5. Obtain formal approval and disseminate to all personnel 6. Update SSP and SCTM to reflect RA-1 as Implemented 7. Close OIS-POA-017 and notify AO of closure | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ Risk Management Team ¦ NIST SP 800-53 RA-1 ¦ NIST SP 800-30 ¦ FedRAMP RA Requirements | Open | Finding identified during SCTM development. FIPS 199 categorization, SCTM, and gap analysis constitute informal risk assessment activities. Formal policy required before RA-3 formal risk assessment can be completed.
Phase 2 — Operational Plans and Configurations
OIS-POA-011 | IR-4 | Formal incident response procedures document has not been written or approved. The seven phase IR lifecycle is operationally understood but no documented procedures exist for detection, containment, eradication, recovery, or post-incident review. | HIGH | 60 days from authorization kickoff | 1. Complete IR-1 policy document as prerequisite 2. Assemble IR procedures drafting team — ISSO, IR team members, AWS administrators 3. Document detection procedures — CloudWatch alert thresholds, CloudTrail review schedule 4. Document containment procedures — IAM account disabling, VPC isolation, WAF blocking 5. Document eradication and recovery procedures for common incident types 6. Document US-CERT one hour reporting procedure with contact information 7. Document AAR process and POA&M update procedures 8. Obtain formal approval from Program Manager 9. Conduct tabletop exercise to validate procedures 10. Update SSP and SCTM ¦ Close OIS-POA-011 | Ashley Miller — ISSO | ISSO ¦ IR Team ¦ AWS Administrators ¦ AWS CloudWatch Console ¦ AWS CloudTrail Console ¦ AWS IAM Console ¦ AWS VPC Console ¦ AWS WAF Console ¦ NIST SP 800-61 Rev 2 ¦ US-CERT Contact Information | Open | Finding identified during SCTM development. Dependent on OIS-POA-010 IR-1 policy completion. AWS detection and containment tools are operational. Formal procedures document does not exist.
OIS-POA-012 | IR-5 | No formal incident tracking log or ticketing system has been established. Security events are captured in CloudTrail and CloudWatch but are not being formally documented with severity ratings, timelines, and resolution status. | MODERATE | 60 days from authorization kickoff | 1. Complete IR-1 policy as prerequisite 2. Define incident tracking log format — ID, date, severity, description, status, resolution 3. Select tracking platform — ServiceNow, spreadsheet, or equivalent 4. Configure tracking system and establish ISSO access 5. Document incident logging procedures 6. Train IR team on incident documentation requirements 7. Update SSP and SCTM ¦ Close OIS-POA-012 | Ashley Miller — ISSO | ISSO ¦ IR Team ¦ ServiceNow or Equivalent Tracking Platform ¦ NIST SP 800-61 Rev 2 Incident Categorization Guidance | Open | Finding identified during SCTM development. CloudTrail captures event data but no formal incident tracking log exists. Dependent on IR-1 policy completion.
OIS-POA-013 | IR-8 | No formal Incident Response Plan document has been developed or approved. The IR Plan must define roles, severity criteria, communication procedures, US-CERT reporting, and annual testing requirements. | HIGH | 60 days from authorization kickoff | 1. Complete IR-1 policy and IR-4 procedures as prerequisites 2. Assemble IR Plan drafting team — ISSO, Program Manager, IR team, Legal 3. Draft IR Plan covering purpose, scope, roles, severity classification, notification procedures 4. Document US-CERT one hour reporting requirement and contact procedures 5. Document relationship to continuity and disaster recovery plans 6. Define annual IR Plan review and update schedule 7. Obtain formal approval from Program Manager and AO 8. Conduct tabletop exercise to validate the plan 9. Document tabletop results and incorporate lessons learned 10. Update SSP and SCTM ¦ Close OIS-POA-013 | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ IR Team ¦ Legal/Compliance ¦ NIST SP 800-61 Rev 2 ¦ US-CERT Contact Information and Reporting Portal ¦ Tabletop Exercise Facilitation | Open | Finding identified during SCTM development. Dependent on IR-1 policy and IR-4 procedures completion. Highest documentation risk — no IR Plan means no documented organizational response authority.
OIS-POA-015 | CM-2 | No baseline configuration document exists for any OIS-CMS component. Technical configurations are in place and operationally correct but have never been formally documented. Without a baseline the organization cannot detect configuration drift or rebuild accurately following a failure. | HIGH | 60 days from authorization kickoff | 1. Complete CM-1 policy as prerequisite 2. Assemble configuration documentation team — ISSO, AWS administrators, application team 3. Log into AWS console and document current configuration for each component 4. Document Elastic Beanstalk environment configuration and security settings 5. Document RDS configuration — encryption, subnet placement, security group rules 6. Document VPC configuration — subnets, route tables, internet gateway settings 7. Document Security Group rules for each component 8. Document WAF rule configuration 9. Document AWS IAM configuration — roles, policies, permission boundaries 10. Compile into formal baseline configuration document and obtain approval 11. Establish change detection monitoring through AWS Config 12. Update SSP and SCTM ¦ Close OIS-POA-015 | Ashley Miller — ISSO | ISSO ¦ AWS Administrators ¦ Application Team ¦ AWS Management Console ¦ AWS Config Service ¦ DISA STIG Benchmarks ¦ Screenshot and Export Tools for Configuration Evidence | Open | Finding identified during SCTM development. All configurations are operationally in place. Formal documentation does not exist. AWS Config can automate ongoing configuration tracking once baseline is documented.
OIS-POA-018 | RA-3 | No formal risk assessment document following NIST SP 800-30 methodology has been produced. No defined assessment frequency or review schedule has been established. Risk assessment activities have been conducted informally as part of the RMF process. | MODERATE | 60 days from authorization kickoff | 1. Complete RA-1 policy as prerequisite 2. Assemble risk assessment team — ISSO, Program Manager, technical SMEs 3. Follow NIST SP 800-30 methodology — identify threat sources, threat events, vulnerabilities 4. Assess likelihood and impact for each identified risk 5. Document risk assessment results in formal report 6. Define risk assessment review schedule — annual minimum 7. Obtain formal approval from Program Manager 8. Update SSP and SCTM ¦ Close OIS-POA-018 | Ashley Miller — ISSO | ISSO ¦ Program Manager ¦ Technical SMEs ¦ NIST SP 800-30 Risk Assessment Methodology ¦ SCTM and Gap Analysis as Input Documents ¦ Risk Assessment Template | Open | Finding identified during SCTM development. FIPS 199 categorization, SCTM, and POA&M constitute informal risk assessment components. Formal NIST SP 800-30 compliant document required.
OIS-POA-019 | RA-5 | No formal vulnerability scanning schedule has been defined. No scan report archive exists. No remediation SLA framework has been established for Critical and High findings. AWS Inspector capability exists but has not been formally configured as a program. | MODERATE | 60 days from authorization kickoff | 1. Complete RA-1 policy as prerequisite 2. Configure AWS Inspector for automated vulnerability scanning across all OIS-CMS components 3. Define scanning schedule — weekly automated scans minimum 4. Define remediation SLAs — Critical: 15 days, High: 30 days, Moderate: 90 days 5. Establish scan report archive in designated S3 bucket 6. Configure AWS Security Hub to aggregate findings 7. Define vulnerability remediation tracking process with assigned owners 8. Document complete vulnerability management program 9. Conduct initial baseline scan and document results 10. Update SSP and SCTM ¦ Close OIS-POA-019 | Ashley Miller — ISSO | ISSO ¦ AWS Administrators ¦ AWS Inspector ¦ AWS Security Hub ¦ AWS S3 (report archive) ¦ Remediation Tracking Platform ¦ CISA KEV Catalog Reference | Open | Finding identified during SCTM development. AWS Inspector is available in the GovCloud environment. Formal scanning program with schedule, SLAs, and tracking has not been established.
Phase 3 — Procedures and Documentation Gaps
OIS-POA-002 | AC-2 | Formal account management procedures document has not been written or approved. The account management process is operationally in place — 90-day reviews, HR-triggered workflow, CloudTrail logging — but no documented procedures exist. | MODERATE | 90 days from authorization kickoff | 1. Complete AC-1 policy as prerequisite 2. Assemble procedures drafting team — ISSO, IAM team, HR system administrators 3. Document account creation procedures — request, approval, provisioning steps 4. Document account review procedures — 90-day schedule, review criteria, documentation requirements 5. Document account modification procedures — request, approval, implementation 6. Document account removal procedures — HR trigger, 24-hour disable, 72-hour removal 7. Obtain formal approval from Program Manager 8. Update SSP and SCTM ¦ Close OIS-POA-002 | Ashley Miller — ISSO | ISSO ¦ IAM Team ¦ HR System Administrators ¦ AWS IAM Console ¦ HR Workflow System ¦ Approved AC-1 Access Control Policy | Open | Finding identified during SCTM development. Account management process is operationally correct. Formal procedures document does not exist. Dependent on AC-1 policy completion.
OIS-POA-004 | IA-5 | Authenticator management procedures document has not been formally written or approved. PIV/CAC cards are issued and operational. AWS KMS manages cryptographic keys. No documented procedures govern the full authenticator lifecycle. | MODERATE | 90 days from authorization kickoff | 1. Complete IA-1 policy as prerequisite 2. Document PIV/CAC card issuance procedures — request, verification, issuance, activation 3. Document PIN management procedures — initial set, reset, expiration 4. Document lost or compromised authenticator procedures 5. Document KMS key rotation schedule and procedures 6. Obtain formal approval from Program Manager 7. Update SSP and SCTM ¦ Close OIS-POA-004 | Ashley Miller — ISSO | ISSO ¦ IAM Team ¦ PIV/CAC Issuance Authority ¦ AWS KMS Console ¦ AWS KMS Documentation ¦ Approved IA-1 Authentication Policy | Open | Finding identified during SCTM development. PIV/CAC operational. KMS managing keys. No procedures document governing full authenticator lifecycle exists. Dependent on IA-1 policy.
OIS-POA-006 | AU-6 | No formal audit review schedule or reporting procedures have been documented. CloudTrail and CloudWatch are generating audit data. The ISSO is informally reviewing logs but no defined frequency, reporting thresholds, or escalation criteria have been established. | MODERATE | 90 days from authorization kickoff | 1. Complete AU-1 policy as prerequisite 2. Define formal audit review schedule — weekly CloudTrail, monthly CloudWatch 3. Define reportable event thresholds and escalation criteria 4. Document audit review procedures — what to look for, how to document findings 5. Define reporting format and recipients for audit findings 6. Obtain formal approval from Program Manager 7. Conduct first formal documented audit review 8. Update SSP and SCTM ¦ Close OIS-POA-006 | Ashley Miller — ISSO | ISSO ¦ Security Operations Team ¦ AWS CloudTrail Console ¦ AWS CloudWatch Console ¦ Approved AU-1 Audit Policy ¦ Audit Review Template | Open | Finding identified during SCTM development. Audit tools operational. No formal review schedule or procedures exist. Dependent on AU-1 policy completion.
OIS-POA-007 | AU-11 | Formal log retention policy has not been documented. AWS S3 object lock and versioning are available but 12-month retention has not been formally configured, validated, or evidenced in writing. | MODERATE | 90 days from authorization kickoff | 1. Complete AU-1 policy as prerequisite 2. Document 12-month minimum retention requirement citing NIST AU-11 and FISMA 3. Configure AWS S3 object lock on CloudTrail log bucket — 12-month retention period 4. Enable versioning on the log storage bucket 5. Capture configuration screenshots as evidence 6. Document retention policy and configuration in formal procedures document 7. Obtain formal approval from Program Manager 8. Update SSP and SCTM ¦ Close OIS-POA-007 | Ashley Miller — ISSO | ISSO ¦ AWS Administrators ¦ AWS S3 Console ¦ AWS CloudTrail Console ¦ Approved AU-1 Audit Policy ¦ NIST AU-11 and FISMA Retention Requirements | Open | Finding identified during SCTM development. S3 retention capability exists. Formal configuration, documentation, and evidence of 12-month retention not yet established.
OIS-POA-009 | SC-12 | Key rotation schedule has not been formally defined or documented. AWS KMS is operational using FIPS 140-2 validated modules. No key management procedures document exists governing rotation schedules, access policies, and usage monitoring. | MODERATE | 90 days from authorization kickoff | 1. Complete SC-1 policy as prerequisite 2. Define key rotation schedule for all OIS-CMS encryption keys 3. Configure automated key rotation in AWS KMS 4. Document key access policies — who can use each key and for what purpose 5. Document key usage monitoring procedures through CloudTrail 6. Document procedures for compromised key response 7. Obtain formal approval from Program Manager 8. Update SSP and SCTM ¦ Close OIS-POA-009 | Ashley Miller — ISSO | ISSO ¦ AWS Administrators ¦ AWS KMS Console ¦ AWS KMS Documentation ¦ AWS CloudTrail Console ¦ Approved SC-1 Policy ¦ NIST SP 800-57 Key Management Guidance | Open | Finding identified during SCTM development. KMS operational with FIPS 140-2 validated modules. Automated rotation not configured. No procedures document exists.
OIS-POA-016 | CM-6 | Configuration settings are technically in place and appropriately restrictive but have not been formally documented. Without documented configuration settings the organization cannot detect drift or defend its configurations during assessment. | MODERATE | 90 days from authorization kickoff | 1. Complete CM-1 policy and CM-2 baseline configuration as prerequisites 2. Document approved configuration settings for each OIS-CMS component 3. Document TLS version and cipher suite settings 4. Document VPC and security group configuration settings 5. Document WAF rule settings and approved traffic patterns 6. Document IAM permission boundaries and role configurations 7. Establish AWS Config rules to detect deviation from approved settings 8. Obtain formal approval from Program Manager 9. Update SSP and SCTM ¦ Close OIS-POA-016 | Ashley Miller — ISSO | ISSO ¦ AWS Administrators ¦ AWS Management Console ¦ AWS Config Service ¦ Approved CM-1 Policy ¦ Completed CM-2 Baseline Configuration Document ¦ DISA STIG Benchmarks | Open | Finding identified during SCTM development. All settings operationally correct. Formal documentation does not exist. Dependent on CM-1 policy and CM-2 baseline completion.

## Summary Dashboard
OIS-CMS POA&M — Summary Dashboard
19 Findings · 3 Remediation Phases · 90-Day Target to ATO · July 2026
Risk Level | Count | % of Total | Target Timeline
HIGH | 10 | 53% | 30-90 days
MODERATE | 9 | 47% | 90-180 days
Remediation Phase | Findings | Target | Focus Area
Phase 1 — Policy Documents | 7 | 30 days | AC-1, IA-1, AU-1, SC-1, IR-1, CM-1, RA-1 — foundational policy documents
Phase 2 — Operational Plans & Config | 6 | 60 days | IR procedures, IR Plan, IR tracking, Baseline config, Risk assessment, Vuln scanning
Phase 3 — Procedures & Documentation | 6 | 90 days | Account mgmt, Authenticator mgmt, Audit review, Retention, Key rotation, Config settings
ROOT CAUSE ANALYSIS — Why All 19 Findings Exist
OIS-CMS has a functional technical security posture — access enforcement, authentication, boundary protection, encryption, audit logging, and least functionality are all operational. All 19 POA&M findings trace back to a single root cause: the system was operational for two years without a formal authorization, and no governance documentation was ever produced. The technical controls work. The paper trail proving they work does not exist. The remediation strategy is straightforward — build the governance layer around the technical controls that already function correctly, starting with the seven foundational policy documents in Phase 1.
RECOMMENDED REMEDIATION PRIORITY ORDER
# | POA&M ID | Finding | Why This Priority
1 | OIS-POA-010 | IR-1 Incident Response Policy | Highest operational risk — no IR authority or US-CERT reporting obligation documented
2 | OIS-POA-001 | AC-1 Access Control Policy | Foundation for all access control governance
3 | OIS-POA-003 | IA-1 Authentication Policy | Foundation for all authentication governance
4 | OIS-POA-005 | AU-1 Audit Policy | Cannot prove compliance without documented audit program
5 | OIS-POA-008 | SC-1 System & Comms Policy | Foundation for transmission and boundary protection governance
6 | OIS-POA-014 | CM-1 Configuration Mgmt Policy | Cannot manage configuration without documented policy
7 | OIS-POA-017 | RA-1 Risk Assessment Policy | Cannot conduct formal risk assessments without policy
8 | OIS-POA-013 | IR-8 Incident Response Plan | Highest documentation risk after policies — no documented response authority
9 | OIS-POA-015 | CM-2 Baseline Configuration | Cannot detect configuration drift without documented baseline